## Summary
Week 7 — Agile metrics
Example results are simulated. Actual results require verified sprint data.
Example sprint | Velocity SP | Not Done SP | Avg lead (d) | Avg cycle (d) | Flow items
Todo | 24 | 0 | 3.2857 | 1.5714 | 7
Study | 15 | 0 | 3.2 | 1.8 | 5
Different project scope and uncalibrated points: do not infer faster/slower performance.
Actual sprint | Velocity SP | Not Done SP | Avg lead (d) | Avg cycle (d) | Flow items
Todo | n.a. | n.a. | n.a. | n.a. | 0
Study | n.a. | n.a. | n.a. | n.a. | 0
n.a. = missing or inconsistent inputs, not zero completed work.
Flow items = Done rows with valid Request <= Start <= Done dates and evidence.
How to use
1. Fill yellow cells in Actual. Keep the Example sheet labelled as simulated.
2. Use Done only after Definition of Done is met; attach a review/checklist reference.
3. Enter status as of Sprint end. A story completed later is Not Done for this sprint.
4. Record dates consistently; blank dates stay unavailable, not zero duration.
5. Read Thai explanations, refinement and video outline in docs/week7/README.md.
Full figures and 12-item calculations: LAB7-1.md to LAB7-3.md.
Story before/after, acceptance criteria and Ready checks: LAB7-4.md.

## Example
Example sprint data — SIMULATED
D0–D5 are illustrative day numbers; each sprint has its own day scale.
Source: docs/week6/LAB6-1.md and LAB6-4.md. Example request/start days are additional assumptions.
Sprint | ID | Backlog item | Points | Status at end | Request | Start | Done | Sprint end | Owner | Blocker | Evidence | Velocity SP | Lead days | Cycle days | Wait days
Todo | TD-01 | Todo CRUD and completion | 3 | Done | 0 | 0 | 1 | 5 | S1 | None in example | SIMULATED, not team evidence | 3 | 1 | 1 | 0
Todo | TD-02 | Save data per account | 3 | Done | 0 | 1 | 3 | 5 | S1 | Illustrative blocker | SIMULATED, not team evidence | 3 | 3 | 2 | 1
Todo | TD-03 | Demo registration / login | 5 | Done | 0 | 1 | 3 | 5 | S2 | Illustrative blocker | SIMULATED, not team evidence | 5 | 3 | 2 | 1
Todo | TD-04 | Recovery code and session | 5 | Done | 0 | 2 | 4 | 5 | S2 | None in example | SIMULATED, not team evidence | 5 | 4 | 2 | 2
Todo | TD-05 | Theme / font / reset | 3 | Done | 1 | 3 | 4 | 5 | S3 | Illustrative blocker | SIMULATED, not team evidence | 3 | 3 | 1 | 2
Todo | TD-06 | Search and status filter | 3 | Done | 0 | 3 | 5 | 5 | S4 | Illustrative blocker | SIMULATED, not team evidence | 3 | 5 | 2 | 3
Todo | TD-07 | Sort and clear completed | 2 | Done | 1 | 4 | 5 | 5 | S4 | Illustrative blocker | SIMULATED, not team evidence | 2 | 4 | 1 | 3
Study | SP-01 | Subjects and exam dates | 3 | Done | 0 | 0 | 1 | 5 | S1 | None in example | SIMULATED, not team evidence | 3 | 1 | 1 | 0
Study | SP-02 | Study session CRUD | 5 | Done | 0 | 1 | 3 | 5 | S2 | Illustrative blocker | SIMULATED, not team evidence | 5 | 3 | 2 | 1
Study | SP-03 | Completion and time totals | 2 | Done | 0 | 2 | 4 | 5 | S3 | None in example | SIMULATED, not team evidence | 2 | 4 | 2 | 2
Study | SP-04 | Search / filter / date order | 2 | Done | 1 | 3 | 4 | 5 | S3 | Illustrative blocker | SIMULATED, not team evidence | 2 | 3 | 1 | 2
Study | SP-05 | Browser persistence | 3 | Done | 0 | 2 | 5 | 5 | S4 | Illustrative blocker | SIMULATED, not team evidence | 3 | 5 | 3 | 2
Lead = Done - Request; Cycle = Done - Start; Wait = Start - Request. No inclusive +1.
Cycle includes blocked/review time after work starts; it is not hands-on coding time.
12 rows are preconfigured. For more items extend formulas, validations and Summary ranges together.

## Actual
Actual sprint data — enter verified evidence
Yellow cells are inputs. Unknown is not zero. Dates must be real Excel dates.
Source: docs/week6/LAB6-1.md and LAB6-4.md. Example request/start days are additional assumptions.
Sprint | ID | Backlog item | Points | Status at end | Request | Start | Done | Sprint end | Owner | Blocker | Evidence | Velocity SP | Lead days | Cycle days | Wait days
Todo | TD-01 | Todo CRUD and completion |  | Unknown | [7 empty] | n.a. | n.a. | n.a. | n.a.
Todo | TD-02 | Save data per account |  | Unknown | [7 empty] | n.a. | n.a. | n.a. | n.a.
Todo | TD-03 | Demo registration / login |  | Unknown | [7 empty] | n.a. | n.a. | n.a. | n.a.
Todo | TD-04 | Recovery code and session |  | Unknown | [7 empty] | n.a. | n.a. | n.a. | n.a.
Todo | TD-05 | Theme / font / reset |  | Unknown | [7 empty] | n.a. | n.a. | n.a. | n.a.
Todo | TD-06 | Search and status filter |  | Unknown | [7 empty] | n.a. | n.a. | n.a. | n.a.
Todo | TD-07 | Sort and clear completed |  | Unknown | [7 empty] | n.a. | n.a. | n.a. | n.a.
Study | SP-01 | Subjects and exam dates |  | Unknown | [7 empty] | n.a. | n.a. | n.a. | n.a.
Study | SP-02 | Study session CRUD |  | Unknown | [7 empty] | n.a. | n.a. | n.a. | n.a.
Study | SP-03 | Completion and time totals |  | Unknown | [7 empty] | n.a. | n.a. | n.a. | n.a.
Study | SP-04 | Search / filter / date order |  | Unknown | [7 empty] | n.a. | n.a. | n.a. | n.a.
Study | SP-05 | Browser persistence |  | Unknown | [7 empty] | n.a. | n.a. | n.a. | n.a.
Lead = Done - Request; Cycle = Done - Start; Wait = Start - Request. No inclusive +1.
Cycle includes blocked/review time after work starts; it is not hands-on coding time.
12 rows are preconfigured. For more items extend formulas, validations and Summary ranges together.